

Our Safety

Our Future

Tasmanian Road Safety Strategy 2007-2016

Progress Report

*to the*

*Road Safety Advisory Council*

*including progress on the Work Program*

*as at*

*31 DECEMBER 2016*

|  |  |
| --- | --- |
| Executive Summary |  |
| Progress on meeting the Tasmanian Road Safety Strategy targets | 4 |
| Progress on meeting the MAIB targets | 6 |
| Key achievements since last report | 7 |
| Strategic Direction 1 – Safer Travel Speeds |  |
| Road Safety Levy Funded Projects |  |
| Fixed Speed Cameras – Information Signage | 9 |
| Strategic Direction 2 – Best Practice Infrastructure |  |
| Road Safety Levy Funded Projects |  |
| Esk Main Road Shoulder Sealing, Edge Lining and Safety Improvements | 10 |
| Motorcycle Safety Package – Infrastructure Safety Improvements | 11 |
| Safer Roads: Vulnerable Road User Program | 13 |
| East Derwent Highway, Old Beach – Cassidy’s Road to Baskerville Road | 16 |
| Midland Highway Safety Improvements | 18 |
| Lyell Highway, south of Hamilton – Shoulder Sealing | 20 |
| Strategic Direction 3 – Improved Safety for Young Road Users |  |
| Road Safety Levy Funded Projects |  |
| Learner Driver Mentor Program Grant Funding | 21 |
| Rotary Youth Driver Awareness Program | 22 |
| Back to school campaign | 23 |
|  |  |


|  |  |
| --- | --- |
| Strategic Direction 4 – Enhanced Vehicle Safety |  |
| Road Safety Levy Funded Projects |  |
| Australasian New Car Assessment Program | 24 |
|  |  |
| Strategic Direction 5 – Complementary Initiatives (Road Users) |  |
| Road Safety Levy Funded Projects |  |
| Mandatory Alcohol Interlock Program (MAIP) | 25 |
| MAIP Review | 26 |
| RSAC and TRSS Support | 27 |
| Development of ‘the Towards Zero’ – Tasmanian Road Safety Strategy 2017-2026 | 28 |
| Driver Mentoring Tasmania | 29 |
| Motorcycle Safety Package | 30 |
| Distance Makes a Difference - Cyclists Public Education Campaign | 34 |
| Tourist Safety | 35 |
| Community Road Safety Grants Program | 38 |
| Discretionary Activities Fund | 39 |
| Funding | 40 |
| Statistics | 42 |

Progress on meeting the Tasmanian Road Safety Strategy targets

* The number of serious casualties in 2016 was 316, compared to 331 in 2015, a 4.5 per cent decrease. The 2016 figure of 316 is a six per cent increase on the five year serious casualty average of 298 (2011-2015).
* For the 2016 calendar year, there were 37 fatalities on Tasmanian roads which is four more than the 33 recorded in 2015. This is a 19 per cent increase on the five year fatalities average of 31.2 (2011-2015).
* The table below outlines road crash deaths for individual states and territories for the period 2005 to 2016.

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **NSW** | **VIC** | **QLD** | **SA** | **WA** | **TAS** | **NT** | **ACT** | **AUST** |
| **2005** | **508** | **346** | **330** | **148** | **163** | **51** | **55** | **26** | **1,627** |
| **2006** | **496** | **337** | **335** | **117** | **200** | **55** | **45** | **13** | **1,598** |
| **2007** | **435** | **332** | **360** | **124** | **235** | **45** | **58** | **14** | **1,603** |
| **2008** | **374** | **303** | **328** | **99** | **205** | **39** | **75** | **14** | **1,437** |
| **2009** | **454** | **290** | **331** | **119** | **191** | **63** | **31** | **12** | **1,491** |
| **2010** | **405** | **288** | **249** | **118** | **193** | **31** | **50** | **19** | **1,353** |
| **2011** | **364** | **287** | **269** | **103** | **179** | **24** | **45** | **6** | **1,277** |
| **2012** | **369** | **282** | **280** | **94** | **183** | **31** | **49** | **12** | **1,300** |
| **2013** | **333** | **243** | **271** | **98** | **162** | **35** | **37** | **7** | **1,187** |
| **2014** | **307** | **248** | **223** | **107** | **183** | **33** | **39** | **10** | **1,150** |
| **2015** | **350** | **252** | **243** | **102** | **160** | **33** | **49** | **15** | **1,205** |
| **2016** | **384** | **292** | **250** | **89** | **193** | **37** | **45** | **9** | **1,300** |
| **% change 2015-16** | **9.7%** | **15.9%** | **2.9%** | **-12.7%** | **20.6%** | **12.1%** | **-8.2%** | **-40%** | **7.9%** |

* The first target of ‘by 2010: a 20% reduction in serious injuries and fatalities from 2005’ has been reached with a reduction of 32%. Progress is indicated on the chart below.
* The second target of ‘by 2015: a 20% reduction in serious injuries and fatalities from 2010’ has not been met. Reasons for this include the fact that the number of serious casualties recorded in 2010 was the second lowest recorded, combined with the fact that since 2012 the number of serious casualties has been gradually increasing.





* The method above, used to determine the TRSS target, compares points in time – a comparison between the year 2005 and the year 2010 and between 2010 and 2015.
* As an additional measure, the five year averages (and part thereof) are included below. This methodology smooths out anomalies between individual years and provides a holistic picture of serious casualties in Tasmania


|  |  |  |  |
| --- | --- | --- | --- |
| **Five year average timeframe** | **Average** | **% of change** | **Period** |
| Annual average of serious casualties 2001 - 2005 | 457.6 | N/A | Baseline period |
| Annual average of serious casualties 2006 – 2010 | 340.4 | - 25.6 | Period 1 |
| Annual average of serious casualties 2011 – 2015 | 297.8 | -12.5 | Period 2 |

## Progress on meeting the MAIB targets

* MAIB injury statistics show the number of fatalities and the level of claims for injuries on our roads. The charts below show the forecast level of claims for serious injuries.
* Various claim reduction targets are specified in the Memorandum of Understanding with the Motor Accidents Insurance Board (MAIB). Progress against high level targets is shown below, expressed as 12-month moving totals.



****



## Key achievements since last report

Key project milestones

* The new *Towards Zero – Tasmanian Road Safety Strategy 2017-2026 (Towards Zero Strategy)* and *Towards Zero Action Plan 2017-2019 (Action Plan 2017-2019)* was launched on 19 December 2016.
* The Motorcycle Training Review of the Motorcycle Safety Package is now complete. The Motorcycle Training Implementation Project team are progressing with the implementation including the transitional arrangements.

Projects completed this quarter

* Securing loads on light vehicle campaign.

**Project progress: schedule and budget**

Budget information, milestones and project status are correct as at 31 December 2016.

|  |  |
| --- | --- |
| **Project progress** | **Number of projects** |
| More than 12 months late | 0 |
| Between 6 and 12 months late | 0 |
| Between 3 and 6 months late | 0 |
| Less than 3 months late or on target | 19 |
| Ongoing | 3 |
| Completed | 1 |
| On hold | 0 |
| **TOTAL** | 22 |

Road Safety Levy Funded Project

1997 Fixed Speed Cameras – Information Signage

Description

With the installation of the new fixed speed cameras, it is timely to review the network of signs across the State. There is an existing network of approximately 16 general information ‘*Red Light and Speed Cameras Operate in Tasmania*’ signs placed on major arterial routes around Tasmania; installed in 1992, these are ageing and in varying conditions of repair.

In August 2015 RSAC agreed to allocate funds for the installation of new speed camera information signs at the ports of entry and in the vicinity of the newly installed cameras; it was also agreed to remove the existing ageing speed camera signage to ensure a consistent approach to signing across the State.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| December 2015 | Install new signs in vicinity of newly installed fixed speed cameras | December 2015 | Completed |
| March 2016 | Install new signs at the five ports of entry | March 2016 | Final camera installed |
| April 2016 | Remove all existing ‘red light and speed cameras operate in Tasmania’ signs | June 2016 | All signs removed |
|  |  | September 2016 | Gateway signs delayed to second quarter |
|  |  | December 2016 | Gateway signs to be installed next quarter. |

Status

Gateway signs at the five ports-of-entry will be installed in the next quarter.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **50,000** | |
| Expenditure in 2015/16 | 16,999 | |
| Expenditure in 2016/17 to date | 0 | |
| **Total expenditure to date** | **16,999** | |
| **Current Balance** | **33,001** | |
| **Forecast total expenditure on completion** |  | **50,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Road Safety Levy Funded Project**

**R10081 Esk Main Road Shoulder Sealing, Edge Line Marking and Safety Improvements**

**Description**

Esk Main Road is the principal route to the East Coast from the Midland Highway and is a significant collector, carrying freight and commuters between regional communities.

The lack of sealed shoulders along sections of the Esk Main Road is a recognised deficiency in the State Arterial Road Network and is the highest priority road for shoulder sealing. Crash analysis for the 20 km section of the highway between Midland Highway and west of Avoca indicates that off-road-on-curve is the major crash type occurring along the road, resulting in a high injury rate of 60%.

Works to be undertaken include shoulder sealing, provision of edge lines and safety improvements. These works will be undertaken in two stages.

Stage 1: Develop a method-based contract, instead of standard detail design contract, over a 3.6km section of the Esk Main Road from the junction with the Midland Highway. Work for Stage 1 will be undertaken through a variation to an existing contract for Esk Main Road improvements, awarded under the Community Roads Program.

Stage 2: Successful methodology applied in Stage 1 will enable shoulder sealing to be delivered more efficiently and cost effectively between Midland Highway and Avoca.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
|  | Stage 3 | June 2016 | Tender for Stage 3 prepared and will be released in July |
|  |  | September 2016 | Tender release delayed to first week of October |
|  |  | Dec 2016 | Contract awarded |

**Status**

Stage 3: Contract awarded and work to commence January 2017.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **5,860,000** | |
| Expenditure in 2012/13 | 208,386 |  |
| Expenditure in 2013/14 | 848,541 |  |
| Expenditure in 2014/15 | 2,716,272 |  |
| Expenditure in 2015/16 | 742,228 |  |
| Expenditure in 2016/17 to date | 34,861 |  |
| **Total expenditure to date** | **4,550,288** | |
| **Current Balance** | **1,309,712** | |
| **Forecast total expenditure on completion** |  | **5,323,500** |
| **Forecast balance remaining on completion** |  | **536,500** |

**Comments**

Significant site constraints have resulted in the project’s scope being reduced; savings have been reallocated to the Lyell Highway shoulder sealing project.

**Road Safety Levy Funded Project**

**R10179 Motorcycle Safety Package – Infrastructure Safety Improvements**

**Description**

The Hodgman Government made a commitment at the last state election to implement motorcycle safety measures along the Great Eastern Drive (the newly named section of the Tasman Highway from Orford to St Helens). Motorcyclists continue to be over-represented in fatal and serious crashes in Tasmania.

The rollout of motorcycle safety infrastructure treatments is aimed at reducing the risk of injury to motorcyclists in the event of a crash. This initiative has been included in the Strategy’s Third Action Plan, with $300,000 being allocated to the project from the Road Safety Levy over three years (i.e. $100,000 per annum).

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| May 2014 | Motorcycle Safety Working Group Established | May 2014 | Completed |
| October 2014 | Commencement of infrastructure projects for 2014/15 financial year (year 1) | December 2014 | Scoping completed. Work to begin early 2015 |
| April 2015 | Completion of 2014/15 financial year projects (year 1) | March 2015 | Contractor engaged to undertake rub rail and signage works |
| July 2015 | Identification and endorsement of 2015/16 projects (year 2) | June 2015 | Rub rail and signage work completed  Scoping for 15-16 work underway |
| October 2015 | Commencement of infrastructure projects for 2015/16 financial year (year 2) | September 2015 | Final scoping and costing for works in Sheffield area completed |
| May 2016 | Completion of 2015/16 financial year projects (year 2) | December 2015 | Executed grant deed sent to Council; work to commence early 2016 |
|  | Safety improvements in Sheffield area underway | March 2016 | Safety improvements in Sheffield area underway |
| July 2016 | Identification and endorsement of 2016/17 projects (year 3) | June 2016 | All work in Sheffield area completed |
| October 2016 | Commencement of infrastructure projects for 2016/17 financial year (year 3) | September 2016 | No additional projects scoped |
|  |  | December 2016 | No additional projects scoped |
| April 2017 | Completion of 2016/17 financial year projects (year 3) |  |  |

**Status**

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **300,000** | |
| Expenditure in 2014/15 | 0 |  |
| Expenditure in 2015/16 | 83,131 |  |
| Expenditure in 2016/17 to date | 3,657 |  |
| **Total expenditure to date** | **86,788** | |
| **Current Balance** | **213,212** | |
| **Forecast total expenditure on completion** |  | **300,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Road Safety Levy Funded Project**

**R10182/R10292 Safer Roads: Vulnerable Road User Program**

**Description**

The Safer Roads: Vulnerable Road User Program has been developed to improve the overall safety of vulnerable road users by minimising the opportunities for conflict between them and motor vehicles. The aim of the program is to reduce serious road crashes involving vulnerable road users. For the purposes of the program, vulnerable road users include pedestrians, cyclists and motorcyclists.

The program is funded at $1.5 million over the two years (2013/14 and 2014/15), and $500 000 a year in future years through the Tasmanian Road Safety Levy (for the life of the Levy, currently to 30 November 2017).

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| April 2013 | Submissions for funding invited | April 2013 | Completed |
| June 2013 | Assessment of submissions and recommendations made to Program Steering Committee | July 2013 | Completed |
| June 2013 | Successful projects for 2013/2014 financial year announced | 30 July 2013 | Announced  11 August 2013 |
| July 2013 | Commencement of projects for 2013/14 financial year | September 2013 | Many projects to be underway during October-December reporting quarter |
| July 2013 | Commencement of projects for 2013/14 financial year | December 2013 | Three projects underway |
| February 2014 | New round of submissions & assessment for projects commencing in financial year 2014/15 | March 2014 | Three projects completed; 10 underway |
| May 2014 | Assessment of submissions and recommendations made to Program Steering Committee | June 2014 | Submissions assessed with advice to councils in July |
| June 2014 | Projects for the 2013/14 financial year to be completed | June 2014 | 9 projects completed; 5 delayed; 2 reviewed |
| June 2014 | Successful projects for 2014/2015 financial year announced | June 2014 | Announced August 2014 |
| December 2014 | Final funding provided by State Government for 2013/14 projects after completion audits | September 2014 | 1 project completed; 4 delayed; 1 withdrawn and 1 postponed |
| December 2014 | Remaining projects in 2013-14 year to be completed.  Design plans for 2014-15 year to be finalised | December 2014 | 2 projects completed; 2 almost completed  Final design plans for 2014-15 projects being received. One further project approved for funding |
| March 2015 | Submissions sought for 2015/16 projects | March 2015 | Letters to councils for the 2015-16 year have been sent. Two projects from the 2013-14 year are yet to be completed; 10 out of 12 2014-15 projects are underway |
| April 2015 | 2015/16 submissions close | June 2015 | All submissions received end May |
| May 2015 | Assessment of 2015/16 submissions and recommendations made to Program Steering Committee | June 2015 | Assessment Committee met in June; recommendations to Steering Committee in July |
| June 2015 | Projects for the 2014/15 financial year to be completed | June 2015 | No projects completed |
| June-July 2015 | Meeting of Program Steering Committee (via tele- or video conference) to discuss assessment of 2015/16 applications | September 2015 | Completed |
| July-August 2015 | Successful projects for 2015/16 announced | September 2015 | Completed |
| September 2015 | Commencement of projects for 2015/16 | September 2015 | Seven of the 12 projects in the 2014-15 round have been completed. Detailed plans being submitted for the 2015-16 projects |
| December 2015 | Final funding provided by State Government for 2014/15 projects after completion audits | December 2015 | 11 of the 12 projects have been completed |
|  |  | March 2016 | Final project for 2014/15 round underway |
|  |  | June 2016 | Bike lanes completed; submissions for Round 4 received  Round 3 projects underway |
|  |  | September 2016 | 7 projects completed; 2 to be completed next quarter |
|  |  | December 2016 | All projects in Round 3 completed. Successful projects for Round 4 announced November. |

**Status**

***Round 3 – 2015-16***

All projects completed; final payments to be made next quarter.

***Round 4 – 2016-17***

Letters sent in November to councils who submitted projects under Round 4.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **2,500,000** | |
| Expenditure in 2013/14 | 329,200 |  |
| Expenditure in 2014/15 | 409,920 |  |
| Expenditure in 2015/16 | 575,705 |  |
| Expenditure in 2016/17 to date | 262,069 |  |
| **Total expenditure to date** | **1,576,894** | |
| **Current Balance** | **923,106** | |
| **Forecast total expenditure on completion** |  | **2,500,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Road Safety Levy Funded Project**

**R10260 East Derwent Highway, Old Beach – Cassidy’s Road to Baskerville Road**

**Description**

The ‘Safe System’ approach aims to create safer roadsides to compensate for driver error, using infrastructure improvements. This project will consist of approximately 1.3km of shoulder sealing and the addition of three dedicated right turn lanes at junctions to reduce intersection crashes and reduce the severity of the S-curve near Cassidy’s Road junction.

At this site there were 29 crashes over a five year period (15 casualty crashes; 14 property damage crashes). These occurred in three clusters:

* Nine loss-of-control crashes (three casualty) on the S-curve near Cassidy’s Road;
* Seven loss-of-control crashes (three casualty) on the bend at Melane Road; and
* Three casualty crashes resulting from loss-of-control and five crashes (three casualty) at the Baskerville Road junction.

Shoulder sealing reduces run-off-road crashes by 30% and head on crashes by 15%. Dedicated right turn lanes at junctions reduce rear-end collisions by 60%. Reduces the severity of curves and hence reduces run-off-road crashes by 60%.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| October/early Nov 2010 | Tender award | January 2011 | Awarded February 2011 |
| December 2010 | Commence works | January 2011 | Commenced March 2011. |
| April 2011 | Complete works | September 2011 | Work suspended due to weather and settlement |
| Summer 2011/12 | Final seal | December 2011 | Monitoring land settlement Interim works planned. |
|  |  | March 2012 | Interim reseal of existing road completed |
|  |  | December 2012 | Work to be finalised |
| June 2013 | All work completed | December 2013 | All major work completed |
| June 2013 | All work completed | June 2014 | Contractor considering best approach to batter banks |
| June 2013 | All work completed | September 2014 | All work completed |
|  |  | Dec 2014 | Property boundary adjustments to be finalised |
|  |  | Sept 2015 | Negotiations with private landholder well underway |
|  |  | December 2015 | Property boundary negotiations continuing |
|  |  | March 2016 | Negotiations in final stages |
|  |  | June 2016 | No further progress |
|  |  | September 2016 | No further progress |
|  |  | December 2016 | No further progress |

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **2,000,000** | |
| Expenditure in 2008/09 | 151,543 |  |
| Expenditure in 2009/10 | 91,162 |  |
| Expenditure in 2010/11 | 1,002,227 |  |
| Expenditure in 2011/12 | 90,541 |  |
| Expenditure in 2012/13 | 254,946 |  |
| Expenditure in 2013/14 | 68,037 |  |
| Expenditure in 2014/15 | 149,502 |  |
| Expenditure in 2015/16 | 13,059 |  |
| Expenditure in 2016/17 to date | 1,743 |  |
| **Total expenditure to date** | **1,822,760** | |
| **Current Balance** | **177,240** | |
| **Forecast total expenditure on completion** |  | **2,000,000** |

**Road Safety Levy Funded Project**

R360001 Midland Highway Safety Improvements – Integration with Commonwealth Funding

Description

A program of work is currently being prepared for priority road safety infrastructure improvements along the Midland Highway. Methodology being used is very similar to that endorsed by RSAC in February 2014 for projects to be funded under the Levy.

Projects are being identified by applying the ‘Safe System’ approach, adopted by all state and territory road authorities. The ‘Safe System’ approach recognises that persons will make mistakes, often resulting in crashes and that road infrastructure needs to be designed to take account of these errors. An important objective for safety improvements on the Midland Highway is to achieve a minimum 3 Stars Risk Rating based on AusRAP reporting methodology.

A number of infrastructure treatments are being scoped and planned including:

* installation of median flexible safety barriers and where appropriate edge flexible safety barriers;
* widening shoulders;
* audible edge and centre lines;
* additional climbing and/or overtaking lanes where required;
* junction improvements; and
* road cross-sections for the next generation of heavy vehicles.

***AusRAP Star Rating***

Midland Highway projects are being scoped to meet an AusRAP Rating of 3 stars using the following criteria:

1. where sections of median barrier are to be introduced, it will be important to provide consistency and reduce unnecessary driver confusion when transitioning from sections of road with a median barrier to sections without a median barrier;
2. road improvement projects identified under the Midlands Partnership Agreement;
3. road risk data from AusRAP; and
4. road auditing to ensure best practice infrastructure standards are met.

In November 2014 RSAC agreed that progress on the Midland Highway Safety Improvements Program will be reported on in the Progress Report for each RSAC meeting; with particular emphasis on the Midland Highway projects which have been cash-flowed from the Levy contribution.

|  |
| --- |
| **Milestone Schedule** |
| Ongoing to end of current Road Safety Strategy – November 2017 |

Status

In the 2016-17 year the Levy will contribute to four safety improvement projects:

1. 2 Plus 1 with flexible safety barrier continuing from South of Kempton to Melton Mowbray.
2. 2 Plus 1 with flexible safety barrier at White Lagoon-Mona Vale.
3. Safety improvements through Bagdad.
4. Safety improvements through Mangalore.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **20,000,000** | |
| Expenditure in 2014/15 | 2,043,878 |  |
| Expenditure in 2015/16 | 1,878,744 |  |
| Expenditure in 2016/17 to date | 4,257,755 |  |
| **Total expenditure to date** | **8,180,377** | |
| **Current Balance** | **11,819,623** | |
| **Forecast total expenditure on completion** |  | **20,000,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Comments**

The Commonwealth Government is providing $400 million over ten years under the Infrastructure Investment Program for improvements on the Midland Highway. The funding is contingent on the State providing a co-contribution of 20% of the project value.

In September 2014 RSAC endorsed that $20m from the Road Safety Levy be provided to form part of Tasmania’s commitment to the Midland Highway Program.

In November 2014 RSAC endorsed that the contribution from the Road Safety Levy to the Safety Improvements on the Midland Highway be allocated to a range of projects identified by the Department of State Growth.

**Road Safety Levy Funded Project**

R10075 Lyell Highway, south of Hamilton – Shoulder Sealing

Description

There were nine reported crashes (1 serious injury, 4 minor injury and 4 property damage) on this section of road in the five-year period 1 January 2010 to 31 December 2014. All involved loss-of-control.

Widening the carriageway to provide 3.0 metre wide traffic lanes and 1.0 metre wide sealed shoulders, will significantly reduce the risk of vehicles going into the gravel and losing control. The widening will extend for some 5.5 kilometres. Sealed shoulders have already been provided to the south of the project site.

It will not be possible to provide 1.0 metre wide sealed shoulders past a series of four rock cuttings on the western side of the road, it is envisaged that works along this section of the road will be limited to the provision of a sealed spoon drain.

In addition to the above works a basic right turn facility in accordance with Austroads Guidelines is to be provided at the Hollow Tree Road junction.

Funds are primarily coming from The Safer Roads Program with the Road Safety Levy contributing towards the cost of design and construction. Design will be undertaken in the 2015-16 year with works to be undertaken in the 2016-17 construction period.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
|  |  | March 2016 | Detailed design work progressing |
| May 2016 | Design work completed and request for tender to be released | June 2016 | Design work completed, tender to be released July |
| May 2017 | Project completed | Sept 2016 | Tender period closed 27 July |
|  |  | Dec 2016 | Contract awarded. |

Status

Contract awarded, work commenced November.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **400,000** | |
| Expenditure in 2015/16 | 66,362 |  |
| Expenditure in 2016/17 to date | 1,096 |  |
| **Total expenditure to date** | **67,548** | |
| **Current Balance** | **332,542** | |
| **Forecast total expenditure on completion** |  | **1,272,000** |
| **Forecast balance remaining on completion** |  | **(872,000)** |

**Comments**

Savings from Esk Main Road and Cove Hill Road projects have been reallocated to the Lyell Highway project.

In May/June 2015 approval was given that $1.9m in savings from other projects be reallocated to continue work on Esk Main Road and to co-fund two new projects with the Safer Roads Program: the Cove Hill Road Roundabout and Lyell Highway South of Hamilton shoulder sealing and line marking.

Road Safety Levy Funded Project

2009 Learner Driver Mentor Programs Grant Funding

Description

The Government has allocated $1.5 million over three years (2014 -2017) from the Road Safety Levy to continue to support Learner Driver Mentor Programs (LDMPs) and Driver Mentoring Tasmania (DMT), in recognition of their significant contribution towards assisting disadvantaged learner drivers to enter the licensing system.

Programs can apply for Government funding to establish, consolidate or expand their LDMP, providing a strong business case can be demonstrated.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| November - December 2014 | First Funding Round advertised (6 month funding), applications assessed and applicants notified of outcome | November 2014 | Complete |
| May – June 2015 | Second Funding Round advertised (12 month funding), applications assessed and applicants notified of outcome | May 2015 | Complete |
| November 2015 | Review 5x low performing programs and applications for further 6 month funding | November 2015 | Complete |
| May – June 2016 | Third Funding Round to be advertised (12 month funding), applications to be assessed and applicants to be notified of outcome | July 2016 | Complete |
| February 2017 | Independent Evaluation on benefits of LDMPs |  |  |

Status

An independent evaluation of the LDMP Funding Program is to be undertaken in early 2017.

|  |  |  |
| --- | --- | --- |
| Budget | | |
| Total allocated budget for project | 1,500,000 | |
| Expenditure in 2014/15 | **399,637** |  |
| Expenditure in 2015/16 | **568,083** |  |
| Expenditure in 2016/17 | **579,666** |  |
| Total expenditure to date | **1,547,440** | |
| Current Balance | -47,440 | |

\*NB: $120,000 in funding for DMT is included in this amount.

Road Safety Levy Funded Projects

**2032 Rotary Youth Driver Awareness Program (RYDA)**

**Description**

The Government made an election commitment to provide Rotary Tasmania with $300,000 from road safety levy funding, over four years, to support the ongoing delivery of the RYDA program in Tasmania.

RYDA involves grade 10 students participating in road safety education sessions organised by volunteers from Rotary Tasmania. The sessions are conducted State-wide.

RYDA is a one day course presented to students in mostly off-campus facilities. Students participate in six 40 minute sessions. The topics covered are;

* Stopping Distances
* Hazard Distractions and Risk
* Plan B: Alcohol, Medicines, Fatigue and Driving
* Police – You choose – the choice is yours
* Accidents do happen – Personal stories from accident victims
* My Wheels – Choosing and maintaining a safe vehicle

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| September 2014 | Funding released - $75,000 for 2014/15 | September 2014 | Complete |
| July 2015 | Funding released - $75,000 for 2015/16 | July 2015 | Complete |
| July 2016 | Funding released | July 2016 | Complete |
| July 2016 | Funding released | June 2017 |  |

**Status**

Currently Rotary Tasmania requires $100,000 each year ($75,000 approximately of which is funded from the Road Safety Levy) to conduct RYDA state-wide. In addition to the Government’s funding, Rotary Tasmania has previously attracted funding from RACT and MAIB. As a result of the Government’s funding, Rotary Tasmania has agreed to work in partnership with the State Growth to review and evaluate how the program is organised and conducted within the state in order to achieve greater sustainability into the future.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **300,000** | |
| Total Expenditure to date | **229,250** | |
| **Current Balance** | **70,750** | |
| **Forecast total expenditure on completion (2017/18)** |  | **300,000** |
| **Forecast balance remaining on completion** |  | **0** |

Road Safety Levy Funded Projects

**2033 Back to school 2017 campaign**

**Description**

A campaign to promote road safety in school zones and around school buses, particularly those on country routes. Components:

* A competition that involves playing an online game that includes key campaign messages.
* A television commercial.
* Bus backs on Tasmanian Bus Association buses.
* A media launch by the Minister on Monday 6 February.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| 1 February | Online game/competition live |  |  |
| 1 February | Bus backs installed |  |  |
| 5 February | Television commercial starts |  |  |
| 6 February | Media launch |  |  |
| 19 February | Television commercial ends |  |  |
| 13 March | Competition drawn |  |  |

**Status**

The campaign is ongoing and the competition is drawn in March.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **90,000** | |
| Total Expenditure to date | **36,711** | |
| **Current Balance** | **53,289** | |
| **Forecast total expenditure on completion (2017/18)** |  | **90,000** |
| **Forecast balance remaining on completion** |  | **0** |

Road Safety Levy Funded Project

2015 Australasian New Car Assessment Program (ANCAP)

Description

ANCAP aims to increase consumer awareness of the importance of purchasing a safer vehicle. Levy funds will be allocated annually to ANCAP for this purpose (approximately $11,000 per annum).

|  |
| --- |
| **Milestone Schedule** |
| This funding will be provided on an ongoing basis for the life of the Road Safety Levy |

Status

This is an ongoing program.

|  |  |  |
| --- | --- | --- |
| **Budget** | | |
| **Total allocated budget for project per annum** | **12,500** | |
| Expenditure in 2010/11 | 9,981 |  |
| Expenditure in 2011/12 | 10,310 |  |
| Expenditure in 2012/13 | 10,630 |  |
| Expenditure in 2014/15 | 11,157 |  |
| Expenditure in 2015/16 | 11,380 |  |
| Expenditure in 2016/17 | 11,608 |  |
| **Total expenditure to date** | **65,066** | |

Comments

Since 2010/11 the Road Safety Levy has been used to support ANCAP.

Road Safety Levy Funded Project

2019 Mandatory Alcohol Interlock Program

Description

In July 2013, the former Government introduced the Mandatory Alcohol Interlock Program (MAIP), targeting high-level and repeat drink drivers.

Following discussions with the Joint Standing Committee on Subordinate Legislation, on 27 November 2013 a fee waiver was introduced for those people eligible to participate in the MAIP whose offence occurred prior to 31 July 2013.

|  |  |
| --- | --- |
| **Milestone Schedule** | **Milestone Progress** |
| Transitional arrangement in place while participants whose trigger offences were prior to 31 July 2013 return to the licensing system | |

Status

As at 31 December 2016, 224 MAIP participants were in receipt of the fee waiver. 670 participants who were receiving the fee waiver have now successfully completed the MAIP.

It was originally estimated that up to 1,621 people would be eligible for the fee waiver, costing up to $5 million. Based on current participation rates, it is estimated that the fee waiver will cost around $3.3 million, spread over 7 years from 2013/14 to 2019/20.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| Total allocated budget for project | 5,000,000 | |
| Expenditure in 2013/14 | 427,258 |  |
| Expenditure in 2014/15 | 936,777 |  |
| Expenditure in 2015/16 | 437,106 |  |
| Expenditure in 2016/17 | 134,480 |  |
| Estimated commitment to Provider\* | 133,161 |  |
| Revised forecast total expenditure on completion | 3,300,000 | |
| Total expenditure to date (including Provider commitment) | **2,068,782** | |
| Revised forecast balance remaining on completion | 1,231,218 | |

Comments

\* This figure is based on the reconciliation of outstanding invoices processed during January 2017 by the Agency and invoices remaining under review from the Provider.

Note: Auditing of the fee waiver element of MAIP identified issues with one of the providers which is likely to result in a significant refund to the Agency. This is likely to be due to a billing system issue that the provider has advised the Agency of, which resulted in the Agency receiving no invoices from the provider for a few months. The Agency is working with the provider to resolve this issue as a priority.

The exact balance remaining to be paid to those people in receipt of the fee waiver is dependent upon how many of the people eligible for the fee waiver return to the licensing system and participate in the MAIP.

Road Safety Levy Funded Project

2300 MAIP Review

Description

The review of the MAIP is an initiative under the Third Action Plan of the *Tasmanian Road Safety Strategy 2007-2016*.

The MAIP Review consists of four major components: legislative, financial, policy and evaluation framework.

1. Legislative Framework: to consider the compliance and suitability of the MAIP’s current legislative framework. This includes identifying changes that could improve business processes and remove unnecessary impediments for participants.
2. Financial Sustainability: to consider the short and long term financial sustainability of the MAIP, including identifying key issues affecting the sustainability of the Program. This includes consideration of the current three provider business model, the fee waiver scheme and the current fee structure.
3. Policy Framework: to consider the MAIP’s policy framework within the Program’s current operating model. This includes identifying and recommending potential changes to the MAIP to improve its effectiveness and efficiency.
4. Evaluation Framework: to develop a framework for conducting an outcome and process evaluation of the MAIP. This includes details regarding the timing, potential methodology and data requirements for a future in-depth analysis of the effectiveness (outcome) and efficiency (process) of the MAIP.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| June 2015 | Initial financial modelling | June 2015 | Complete |
| July 2015 | Legislative compliance register complete | July 2015 | Complete |
| August 2015 | Community and participant surveys | August 2015 | Complete |
| August-October 2015 | Stakeholder consultation | September 2015 | Complete |
| November 2015 | Policy Framework report complete |  | Ongoing |
| November 2015 | Legislative Framework report complete |  | Complete |
| November 2015 | Financial Sustainability report complete |  | Ongoing |
| November 2015 | Evaluation Framework report complete |  | Ongoing |
| December 2015 | Recommendations provided to Minister |  | August/September 2015 |

Status

A report outlining the findings of the four components of the MAIP Review, including recommended changes to the program, is currently being finalised.

|  |  |
| --- | --- |
| **Budget ($)** | |
| **Total allocated budget for project** | **TBA** |
| Expenditure in 2015/16 | 7,900 |
| **Total expenditure to date** | 7,900 |
| **Current Balance** |  |

Road Safety Levy Funded Project

2021 RSAC and TRSS Support

Description

Road Safety Levy funding was approved for two positions to assist with the co-ordination and implementation of projects delivered under the Tasmanian Road Safety Strategy, for the life of the Levy. One position is within the Road Safety Branch and one within the Traffic Engineering Branch.

This funding also supports the costs for operation of the Road Safety Advisory Council, including sitting fees for the Chair and expert advice to the Council.

|  |
| --- |
| Milestone Schedule |
| Ongoing |

Status

Support of the RSAC and Tasmanian Road Safety Strategy projects is ongoing.

|  |  |
| --- | --- |
| Budget | |
| **Total allocated budget for project** | **N/A** |
| Expenditure in 2007/08 | 95,017 |
| Expenditure in 2008/09 | 121,411 |
| Expenditure in 2009/10 | 287,119 |
| Expenditure in 2010/11 | 379,972 |
| Expenditure in 2011/12 | 384,448 |
| Expenditure in 2012/13 | 204,448 |
| Expenditure in 2013/14 | 284,028 |
| Expenditure in 2014/15 | 280,740 |
| Expenditure in 2015/16 | 296,960 |
| Expenditure in 2016/17 | 158,383 |
| **Total expenditure to date** | **2,492,526** |

2223 Development of the Towards Zero – Tasmanian Road Safety Strategy 2017-2026

Description

The current *Tasmanian Road Safety Strategy 2007-2016* is nearing the end of its life (end 2016). The current Strategy was developed under the auspices of the former Tasmanian Road Safety Council (TRSC) and provided strategic directions to guide road safety activities in Tasmania over the 10 year period 2007-2016.

The development of the new *Towards Zero –* *Tasmanian Road Safety Strategy 2017-2026* (Towards Zero Strategy) is an initiative identified in the Third Action Plan of the current road safety strategy which was endorsed by the Road Safety Advisory Council and the Minister for Infrastructure.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone Schedule** | | | **Milestone Progress** | | |
| **Date** |  | | **Date** |  | |
| June 2016 | | RSAC Workshop to prioritise actions | June 2016 | Complete |
| June 2016 | | Develop Stakeholder and Public Consultation Report – Stage 2 | June 2016 | Complete |
| July – August 2016 | | Consultation feedback to participants | July 2016 | Complete |
| July - August 2016 | | Draft Strategy and first Action Plan | August 2016 | Complete |
| August 2016 | | Draft Strategy and first Action Plan to RSAC for endorsement | August 2016 | Complete |
| October 2016 | | Cabinet Briefing and final draft strategy to Government for noting | December 2016 | Complete |
| December 2016 | | Launch new strategy | December 2016 | Complete |

Status

Cabinet noted the Towards Zero Strategy and Action Plan 2017-19 as part of a Cabinet Briefing at its 13 December 2016 meeting.

The Towards Zero Strategy and Action Plan 2017-19 was officially launched on 19 December 2016 by the Minister for Infrastructure, in conjunction with the RSAC Chair.

Work will now commence on implementing priority actions under the Action Plan 2017-19.

|  |  |  |
| --- | --- | --- |
| **Budget** | | |
| **Total allocated budget for project** | **400,000** | |
| Expenditure in 2015/16 | 266,488 |  |
| Expenditure in 2016/17 | 40,260 |  |
| **Total expenditure to date** |  | **306,748** |
| **Current Balance** |  | **93,242** |
| **Forecast total expenditure on completion** |  | **400,000** |

Road Safety Levy Funded Project

2026 Driver Mentoring Tasmania Inc

Description

Driver Mentoring Tasmania Inc (DMT), is the peak body representing Learner Driver Mentor Programs (LDMPs) in Tasmania. The Government committed $1.5 million from the road safety levy to continue to support DMT and LDMPs for three years. Of this funding, approximately $120,000 has been provided to DMT each year over three years, to support DMT and in particular to continue the role of the state-wide coordinator.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| July and August 2014 | Grant Deed Established and funds transferred | July 2014 | Complete |
| March 2015 | Commence discussions and development of 2015-16 business priorities and DMT operational plan | March 2015 | Complete |
| June 2015 | Business plan and budget for 2015/16 submitted | June 2015 | Complete |
| July 2015 | Grant Deed established and funds transferred | June 2015 | Completed |
| May 2016 | DMT to provide twelve month Progress Report for the period 2015/16 | May 2016 | Complete |
| June 2016 | Grant Deed Established and funds transferred | July 2016 | Complete |

Status

DMT submitted their Operational Plan to support their submission for funding from the government for the 2016/17 financial year in June 2016. DMT submitted a budget totalling $111,840 (excluding GST) which was accepted.

|  |  |  |
| --- | --- | --- |
| Budget | | |
| Total allocated budget for project |  | |
| Expenditure in 2014/15 | 120,000 |  |
| Expenditure in 2015/16 | 120,000 |  |
| Expenditure in 2016/17 | 111,840 |  |
| Total expenditure to date | 351,840 | |

Road Safety Levy Funded Projects

**2301 Motorcycle Safety Package – Safety Programs and Training**

**Description**

The Hodgman Government made an election commitment to carry out a full review of motorcyclist training and safety programs and have them assessed against best practice in other jurisdictions.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| August 2015 | Expert consultant to be engaged to undertake gap analysis | September 2015 | Gap analysis and recommendation report received and accepted by members of the Motorcycle Safety Working Group |
| October 2015 | Television advertisement targeting motorcycle rider safety to commence for six month period | September 2015 | Endorsed by Motorcycle Safety Working Group |
| October 2015 | Commence arrangements (including seeking Ministerial approval) to engage the University of New South Wales (UNSW) to analyse the applicability of the new Victorian curriculum against Tasmanian crash causes | December 2015 | Complete, endorsement from Minister received 19 October 2015 |
| November 2015 | Commence a review of the current requirements for Assessors/Instructors and review current training assessment locations and range layouts to determine potential impacts | December 2015 | Complete, findings to be outlined in the implementation strategy following the feasibility assessment |
| November 2015 | Seek outcomes from VicRoads regarding the pilot of the new curriculum to gain understanding of any potential issues | June 2016 | Completed |
| December 2015 | UNSW commence crash causation analysis work to determine the applicability of the new Victorian curriculum in Tasmania | June 2016 | Completed |
| March 2016 | Development of a communication strategy that includes a discussion paper to enable the community to provide feedback on any proposed changes | June 2016 | Communication strategy paper currently being scoped. It is anticipated communication activities will be undertaken in stages to ensure consistent messaging. |
| March 2016 | Commence undertaking a feasibility assessment which will include a comprehensive cost analysis to identify impacts to both community, business and Government | June 2016 | Completed |
| July 2016 | Present findings from the crash causation analysis, VicRoads trial results and costs analysis to Minister for future direction | June 2016 | Completed. Final report received from UNSW May 2016. |
| August/ September 2016 | Commence developing an implementation strategy which will include the Motorcycle Assessor/Instructor training strategy and training location transitional plan | June 2016 | Complete. |
| September 2016 | Review expected to be finalised. The Findings and recommendations are to be presented to RSAC and the Minister for consideration | September 2016 | Complete recommendations endorsed by RSAC and the Minister. |
| October/November 2016 | Investigation into reproducing a motorcycle crash card for distribution to Tasmanian motorcycle riders as part of the Motorcycle Summer Safety Campaign | Late October 2016 | Materials sourced from developer and approval to reproduce in Tasmania. However due limited to seek approval from Emergency Services it will be further explored as the 2017 Motorcycle Summer Safety Campaign. |
| October 2016 | Develop implementation plan for existing motorcycle learners. This includes a detailed transitional plan (including the delivery of a “Bridging Course” and an incentive program) as well as a comprehensive communication strategy | October 2016 |  |
| November 2016 | Present the Transitional Plan, including seeking funding for the development of the “Bridging Course” and the incentive program to RSAC and Minister for endorsement | November | Review complete endorsed by RSAC and the Minister. Project Activities being progressed by the Motorcycle Training Implementation Project. |
| December 2016 | Minister announces new Program | 19 December 2016 | Complete |
| December 2016 | Application for Provision of Motorcycle Training and Assessment Services advertised | 21 December 2016 | Complete advertised in Australian, Mercury, Examiner, Advocate. |
| January 2016 | Stage 1 Application for Services closed and evaluated |  |  |
| February 2016 | Stage 2 Application for Services closed and evaluated |  |  |
| March 2016 | Assessor Training |  |  |
| March 2016 | Write directly to those affected by the transitional arrangements |  |  |
| April 2016 | Route and Range Assessments |  |  |

**Status**

The Review has now been finalised. On 13 September 2016, the Minister endorsed the recommendation to adopt the new Victorian Motorcycle Training and Assessment Program (Program) in its entirety in Tasmania (i.e., the new pre-learner curriculum, on-road activity, check ride and learner licence exit test [known as the pre-provisional test in Tasmania]). In addition the Minister endorsed a funding allocation of up to $350,000 from the Road Safety Levy to implement the Program.

On 9 November the Minister endorsed the Transitional Arrangements required to support the implementation of the new Program. The Transitional Arrangements will provide further training to those that obtain a motorcycle learner licence, through the existing scheme, with the higher order riding skills and knowledge required to participate in the new Check Ride and new Pre-Provisional Test to obtain a P1 motorcycle licence.

The additional training (Bridging Course) will essentially be Day 2 of the new Pre-Learner Motorcycle Training Course. Day 2 contains the on-range skills assessment and the on-road coaching and mentoring session.

Motorcycle learner licence holders who obtain a licence prior to 1 January 2017 will be incentivised to participate in the new Bridging Course if they haven’t obtained a P1 licence by 1 July 2017. Those that obtain a motorcycle learner licence from 1 January 2017 (up until 8 May 17) will be mandated to participate in the Bridging Program. These participants will be offered a subsidy from the Road Safety Levy to offset the additional costs.

In addition the Minister endorsed a funding allocation of up to $300,000 from the Road Safety Levy to implement the Transitional Arrangements.

The existing contractual arrangements to deliver the current services are due to expire on 30 June 2017. The Motorcycle Training Implementation Project has been progressing with the Application for Provision of Motorcycle Training and Assessment Services (Application for Services) to enable the selection of sustainable Organisations to deliver the new Program on behalf of the Registrar of Motor Vehicles.

The Application for Services was advertised both in Tasmania and the Mainland on 21 December 2016. Stage 1 of the Application for Services is due to close on 11 January 2017 and successful applicants will be invited to participate in an Information Session, to be held on 24 January 2017.

Stage 2 is due to close on 21 February 2017 with the awarding of contracts to be made around 10 March 2017.

Late March 2017, Assessor Training will commence. A motorcycle training and assessment expert, who played a lead role in the development of the Victorian curriculum and development and delivery of Assessor training, has been identified to deliver this training in Tasmania. This is vital to ensure the highest degree of competency to deliver the new Program by early May 2017.

In mid-April 2017, work will commence with Provider(s) to finalise the new off road ranges to ensure they meet the new range specifications (line markings and layout) and to review the new on-road routes to ensure they comply with the new requirements of the Program.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **200,000** | |
| **Total expenditure to date** | **37,943** | |
| **Current Balance** | **162,057** | |
| **Forecast total expenditure on completion** |  | **200,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Comments**

The Third Action Plan of the *Tasmanian Road Safety Strategy 2007-2016* identifies public education to promote motorcycle safety and a review of training and safety programs for motorcyclists. $200,000 has been allocated from the Road Safety Levy to fund such initiatives.

Road Safety Levy Funded Projects

2235 Distance makes the difference – cyclist safety campaign

Description

RSAC’s Cycling Safety Steering Committee (CSSC) recommended that the Department of State Growth should monitor the Queensland trial of the one metre law over the next two years, and develop a major education campaign encouraging motorists to overtake cyclists with a minimum passing distance of one metre (in speed zones 60km/h and under) and of 1.5 metres (in speed zones greater than 60km/h).

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| **Date** |  | **Date** |  |
| October 2015 | Launch of campaign | 18 October 2015 | Complete |
| August 2016 | Review of one metre law and development of stage 2 of campaign | June 2016 |  |
| August – December 2016 | Ministerial decision on introduction of minimum passing distance legislation | August 2016 | On hold pending decision |

This campaign is the priority project under the Cycling Safety Package. Development of the campaign will be ongoing over a minimum of two years. A wide range of communication tools and media will be used to communicate this key message to road users.

Status

Elements forming the basis of the current phase of the Distance Makes the Difference campaign are bus back advertising, targeted print advertising, sponsorship of Blundstone Arena and sponsorship of the Big Bash Cricket league. These sponsorships have enabled strong reach with targeted audiences both attending games at Blundstone Arena and watching television coverage of the Big Bash Cricket League. Innovative signage opportunities in high traffic areas at Blundstone including signage on the ground at ATM’s, in the men’s toilets and ownership of one of the most prominent signs on the embankment have received positive feedback. The TVC continues to gain traction on social media being viewed 1,471,925 times and shared 3,604 times on one facebook page alone, it has now been viewed 194,022 time on the Department of State Growth website YouTube page. Branded hi-vi vests have been used by marshals at a number of community and sporting events around Tasmania.

Any changes to the law mandating a minimum passing distance of 1 metre will be taken into consideration before stage 2 is developed.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **350,000** | |
| **Total expenditure to date** | **336,497** | |
| **Current Balance** | **13,503** | |
| **Forecast total expenditure on completion** |  | **350,000** |
| **Forecast balance remaining on completion** |  | **0** |

Road Safety Initiatives Funded Project

2302 & 2303 Tourist Safety Strategy

Description

Tourism brings around 1.3 billion Australian dollars into the Tasmanian economy every year. Perceptions of safety and security are an important component in the attractiveness of any tourist destination.

|  |  |  |  |
| --- | --- | --- | --- |
| Milestone Schedule | | **Milestone Progress** | |
| Date |  | Date |  |
| April 2015 | Commence investigation of tourist crashes in Tasmania | April 2015 | Complete |
| May 2015 | Complete investigation of tourist crashes in Tasmania | May 2015 | Complete |
| July 2015 | Develop Strategy and Actions | July 2015 | Complete |
| August 2015 | Tourist Road Safety Strategy (Strategy) and funding endorsed by RSAC | August 2015 | Complete |
| September- October 2015 | Development of Stage 1 initiatives of the Strategy including motorcycle v-log | November 2015 | Complete |
| February 2016 | Review of RSAC endorsed tourist strategy and stage 1 deliverables. Concept development for Stage 2 and budget. | March 2016 | Complete |
| March 2016 | RSAC to note progress and endorse stage 2 | March 2016 | Carried over to August meeting |
| August 2016 | RSAC to note stage 2 campaign and deliverables | August 2016 | Carried over to November meeting |
| November 2016 | RSAC noted stage 2 campaign deliverables and endorsed funding of up to $100k for the second stage | November 2016 | Complete |
| January 2017 | Media event Launceston Airport promoting the campaign, in particular new information being provided in hire cars and signage also | January 2017 | Complete |

Status

State Growth prepared a report for RSAC, investigating the crash rate of interstate and international tourists on Tasmanian roads. The investigation included an in-depth analysis of the available crash data and the Tasmanian Visitor Survey which provides a profile of the characteristics, travel behaviour and expenditure of international and domestic visitors to Tasmania.

Available crash data indicates that between 2010 and 2014, there was a total of 1,249 serious casualty crashes in Tasmania, of these there were 131 crashes involving non-Tasmanian residents.

This means that interstate and international visitors accounted for around 10 per cent of all serious casualty crashes in Tasmania (2010 – 2014). Interstate motorcycle riders made up 46 per cent of tourist serious casualty crashes.

On 19 May 2015, RSAC recommended the development of an evidence-based strategy addressing tourist safety which was endorsed at the 18 August meeting.

The Tourist Road Safety Strategy (Strategy) targets three groups that have a high crash risk whilst visiting Tasmania; interstate motorcyclists, interstate drivers and international drivers. The initiatives contained in the Strategy are designed to be innovative and capitalise on existing tourist networks.

The Strategy is being delivered in two stages.

**Stage one (2015/16):**

**Motorcyclists**

Stage one involved the development of a short video aimed at interstate motorcyclists (motorcycle v-log). The v-log is designed to create awareness of Tasmania’s unique riding conditions and provide practical road safety advice to riders on how to explore Tasmania safely. The video continues to be distributed through tourist networks, including Tasmanian and interstate motorcycle clubs, the Spirit of Tasmania as well as via other key stakeholders, including the RACT.

This video was used to provide information about riding safely in Tasmania to the 4,000 interstate Ulysses motorcycle riders who visited Tasmania in February 2016. Ulysses also assisted with broad dissemination of the v-log.

**International Tourists**

The second part of stage one focused on international tourists and in particular Chinese visitors. Through a partnership with Bridestowe Lavender Farm, ‘Bobbie Bear’ has become the mascot to engage visitors and promote road safety messages. High quality DL flyers continue to be available at airports with life size ‘Bobbie Bear’ cut-outs providing an innovative drawcard to capture visitor attention. The campaign also includes the distribution of posters and DL flyers across the Tasmania’s tourist network.

**Stage Two (2016/17):**

Stage 2 is continuing to engage visitors to promote road safety in Tasmania:

* New road safety information – steering wheel ‘hangers’. These are placed in hire cars and provide key road safety information direct to self-drive visitors to Tasmania.
* Placement of road safety advertising in Chinese related tourist magazines.
* Billboard signage at Launceston and Hobart airports promoting safe driving in Tasmania.
* Production of a new motorcycle safe riding brochure based on the existing Tasmanian Motorcycle Council publication. This new brochure is being distributed to motorcyclists travelling on the Spirit of Tasmania.
* Opportunities for road safety signage for both visiting drivers and motorcyclists is also being pursued.

|  |  |  |
| --- | --- | --- |
| **Budget ($)** | | |
| **Total allocated budget for project** | **150,000** | |
| **Total expenditure to date** | **114,451** | |
| **Current Balance** | **35,549** | |
| **Forecast total expenditure on completion** |  | **150,000** |
| **Forecast balance remaining on completion** |  | **0** |

**Road Safety Levy Funded Project**

**2222 Community Road Safety Grants Program**

**Description**

The Community Road Safety Grants (CRSG) Program seeks to reduce the number of serious casualties on Tasmanian roads each year, through:

* supporting community involvement in addressing local road safety issues and promoting road safety; and
* assisting key road safety stakeholders and the community to develop and implement effective community road safety programs that contribute to positive and sustainable road safety outcomes.

$600,000 has been made available from the Road Safety Levy to support the new CRSG Program over three years, from 2015-16 until 2017-18. Up to $200,000 each financial year has been allocated.

Projects that will be considered for funding under this grants program must be evidence-based, using research or best practice principles. They must address identified localised road safety issues or be of road safety benefit, targeting a specific group or issue and align with the *Tasmanian Road Safety Strategy 2007 – 2016.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Schedule** | | **Milestone Progress** | |
| Date |  | Date |  |
| July – October 2015 | Administer first funding round | October 2015 | Complete |
| Feb – April 2016 | Administer second funding round | July 2016 | Complete |
| June 2017 | Administer third funding round |  |  |

**Status**

A Report is now being prepared collating evaluation and acquittal forms from CRSG recipients of round one.

|  |  |  |
| --- | --- | --- |
| **Budget** | | |
| **Budget for project (3 year program up to $200,000 p/a)** | **600,000** | |
| Expenditure in 2015/16 | 105,087 |  |
| Expenditure in 2016/17 | 86,477 |  |
| **Total expenditure to date** |  | 191,564 |
| **Current Balance** |  | **408,436** |

**Road Safety Levy Funded Project**

**Description**

A Discretionary Activities Fund has been established under the Road Safety Levy as a funding source for discretionary activities including small road safety campaigns, program evaluations, facilitation and attendance at workshops and other small projects within the road safety work program.

|  |  |  |
| --- | --- | --- |
| **Cost Code** | Description | Expenditure |
| 2185 | RSAC Website redevelopment | 7,412 |
| 2186 | Agfest ANCAP crashed car display | 268 |
| 2197 | Safe System Infrastructure Workshop | 10,960 |

|  |  |  |
| --- | --- | --- |
| **Budget** | | |
| **Total allocated budget for project** | **250,000** | |
| Expenditure in 2016/17 | 18,640 |  |
| **Current Balance** | **231,360** | |
| **Forecast total expenditure on completion** |  | **250,000** |
| **Forecast balance remaining on completion** |  | **0** |

## Road Safety Levy 2016/17

As at 31 December 2016

|  |  |  |
| --- | --- | --- |
| **2016/17 Financial Year** | **Proposed Budget 2016/17** | **Actual (ytd) 2016/17** |
| Opening Balance (at 1 July 2016) |  | 16,787,282 |
| **Revenue** |  |  |
| Road Safety Levy collected | 13,100,000 | 6,474,972 |
| Funds available for distribution | 10,500,000 | 3,874,972 |
| **Total Funds available for distribution** | **27,287,282** | **20,662,254** |
|  |  |  |
| **Expenditure** |  |  |
| Safer Travel Speeds |  | 0 |
| Best Practice Infrastructure |  | 443,230 |
| Improved Safety for Young Road Users |  | 579,666 |
| Enhanced Vehicle Safety |  | 11,608 |
| Complementary Initiatives |  | 1,643,944 |
| Discretionary Activities Fund |  | 305,918 |
| **Total** |  | **2,984,366** |
| Closing Balance |  | **17,677,888** |

The above figures include completed projects that are not reported on in this progress report.

## MAIB Funding

As at 31 December 2016

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **2016/17 Financial Year** | **Budget 2016/17** | **Actual 2016/17** |  | **Balance** |
| **Expenditure  (State Growth)** |  |  |  |  |
| Administration & Public Relations | 267,617 | 135,574 |  | 132,043 |
| Public Education | 946,257 | 408,437 |  | 537,820 |
| Research | 62,324 | 16,600 |  | 45,724 |
|  | **1,276,198** | **560,611** |  | **715,587** |
|  |  |  |  |  |
| **Expenditure (Police)** |  |  |  |  |
| Salaries | 1,821,461 | 871,250 |  | 950,211 |
| Operating Expenses | 186,000 | 74,168 |  | 111,832 |
| Equipment | 616,072 | 80,643 |  | 535,429 |
|  | **2,623,533** | **1,026,061** |  | **1,597,472** |
|  |  |  |  |  |
| **Total** | **3,899,731** | **1,586,672** |  | **2,313,059** |

# 

Please note: Budget includes carry forwards of $14,537 to State Growth and $174,417 to Police.


## Statistics Overview


### 2016


* The number of serious casualties in 2016 was 316, compared to 331 in 2015, a 4.5 per cent decrease. The 2016 figure of 316 is a six per cent increase on the five year serious casualty average of 298 (2011-2015).
* For the 2016 calendar year, there were 37 fatalities on Tasmanian roads which is four more than the 33 recorded in 2015. This is a 19 per cent increase on the five year fatalities average of 31.2 (2011-2015).
* Motorcyclists accounted for 29.1% of serious casualties in 2016, 32.6% of serious casualties in 2015 and 25.9% of serious casualties over the five year average. Motorcycles account for approximately 4% of vehicle registrations and approximately 1.5% of vehicle kilometres travelled in Tasmania.
* There were no bicyclist fatalities in 2016, compared to the single fatality recorded in 2015. There were 3 bicyclist serious casualties in 2016, which was 10 fewer than the number recorded in 2015 and down on the 5 year average of 11.6 serious casualties.
* 19 of the 37 fatalities (51%) occurred in 100km/h or 110km/h zones while 74 of the 278 serious injuries (26.6%) occurred in speed zones 60km/h or less.
* The highest contributing crash factors in 2016 were; excessive speed for the conditions/circumstances (24%), alcohol (18.3%), inexperience (17.4%). *Note: more than one crash factor can be attributed to a single crash.*
* Run-off road continues to be the major crash type accounting for 49% of serious casualties, followed by head-on crashes with 20%.

The source is data from Police reports at the time of the crash.












\*Depicts serious casualties where a crash has occurred with the vehicle travelling off path through a curve or off path travelling straight




\*Depicts serious casualties where a crash has occurred between vehicle from opposing directions







\*Depicts serious casualties for drivers of a motor vehicle from 16 – 25 years of age




\*Depicts serious casualties for drivers of a motor vehicle from 65 – 99 years of age




\*Depicts serious casualties where the crash factor of exceeding the speed limit and/or excessive speed for the conditions/circumstances is listed as a contributing factor to the crash. There may be instances where both speed factors are recorded for a single crash.





\*From 1 January 2011 ‘inattentiveness’ will only be reported if there is no other relevant crash factor.





\*Depicts serious casualties where alcohol is listed as a contributing factor














**Serious Casualty locations 2016 (Black = Fatal, Red = Serious Injury)**

